## Milestone Grid
Milestones: Implementation of PSYCKES-Medicaid Program Name: ________________________________ Implementation Kick-Off Date: ____________________
Plan | Task # | Milestone 1: Program Has Committed to Implementing PSYCKES and Implementation Team is Assembled | Person Responsible | Beginning Date | Target Date | Completion Date | Notes
| 1 | Explanation of PSYCKES and use case for organization is explained to key organization leadersion
| 2 | Designate PSYCKES implementation team leadership / PSYCKES point person
| 3 | Designate members of PSYCKES implementation team
| 4 | Engage organization and program leadership and liaisons that will be involved in PSYCKES workflow (e.g. agency Security Manger, IT Staff)
|  | Milestone 2: Implementation Team Has Created Implementation Plan | Person Responsible | Beginning Date | Target Date | Completion Date | Notes
| 5 | Establish internal project management/communication process (e.g. weekly meetings, add to standing agenda for regular meeting, etc.)
| 6 | Finalize implementation timeline and task assignments (milestone document)
Prepare |  | Milestone 3: PSYCKES Policies and Procedures Have Been Developed and Have Received Necessary Approvals | Person Responsible | Beginning Date | Target Date | Completion Date | Notes
| 7 | Program Policies/Procedures are reviewed for compatibility with PSYCKES procedures
| 8 | PSYCKES-specific policies and procedures are developed and documented (use document called "Using PSYCKES for Clinical Purposes: Guidelines for Policies and Procedures" for suggestions)
| 9 | Proposed PSYCKES workflow procedures for the program have been documented, including the "who," "when," and "how" processes for identifying Medicaid enrollees, obtaining consent, documenting consent/emergency access, obtaining PSYCKES data, reviewing PSYCKES reports, and incorporating PSYCKES data into client records
| 10 | Policies and procedures for PSYCKES have necessary adminstrative approvals
| 11 | Any interdepartmental/interdisciplinary work flows have been communicated to and endorsed by other relevant departments (as appropriate)
| 12 | Any desired changes to medical record and/or other internal documentation have been requested
| 13 | Forms are approved for inclusion in client records (including PSYCKES Consent Form and Clinical Summary)
|  | Milestone 4a: PSYCKES Access Has Been Granted to the Agency | Person Responsible | Beginning Date | Target Date | Completion Date | Notes
| 14 | CEO/ED signs PSYCKES Confidentiality Agreement
| 15 | Program completes PSYCKES Access Online Contact Form survey
| 16 | Submit Confidentiality Agreement and PSYCKES Access Online Contact Form survey to PSYCKES team
| 17 | PSYCKES team grants access and informs point persons
Prepare |  | Milestone 4b: All PSYCKES Users Have PSYCKES Access and Have Received Tokens | Person Responsible | Beginning Date | Target Date | Completion Date | Notes
| 18 | Identify SMS security manager
| 19 | If necessary, CEO/ED assigns new/additional security manager
| 20 | Point person coordinating PSYCKES access gathers necessary data from PSYCKES users and passes to Security Mgr; start with members of implementation team and super-users (frequent users)
| 21 | Security Manager assigns PSYCKES access to each user (PSYCKES-Medicaid role)
| 22 | All PSYCKES users received User IDs & tokens (soft tokens installed on users' computers)
|  | Milestone 5: Computers Have Been Prepared for PSYCKES Use | Person Responsible | Beginning Date | Target Date | Completion Date | Notes
| 23 | Designated computers are prepared with internet access, compatible browsers and PDF readers installed
| 24 | All designated computers and/or user desktops have a shortcut to PSYCKES login page
|  | Milestone 6: Relevant staff are trained in PSYCKES use, Enable PHI Access menu use, Policies and Procedures, Confidentiality | Person Responsible | Beginning Date | Target Date | Completion Date | Notes
| 25 | Staff are trained in the use of PSYCKES, including Enable PHI Access menu as required (use "Training Recommendations" document for suggestions)
| 26 | Staff are trained in internal workflow procedures related to PSYCKES use and documentation
| 27 | Staff are trained on HIPAA and other relevant security procedures
| 28 | Staff are trained on language/scripts for requesting consent
Go Live! |  | Milestone 7: Go live! | Person Responsible | Beginning Date | Target Date | Completion Date | Notes
| 29 | PSYCKES workflow and task assignments go into effect: staff begin using PSYCKES and the Enable PHI Access menu for all new admissions with Medicaid and begin consenting current clients
| 30 | Implementation team leads are on site or on call to provide support
| 31 | 90% of eligible clients seen by the program have PSYCKES clinical summaries in their record
Support |  | Milestone 8: Implementation Challenges Have Been Identified and Addressed | Person Responsible | Beginning Date | Target Date | Completion Date | Notes
| 32 | Implementation team leads monitor operations and identify any challenges/barriers
| 33 | Implementation team leads develop and implement a plan for addressing challenges
| 34 | Implementation plan and workflow document are adapted as needed
Sustain |  | Milestone 9: A Plan Has Been Developed for Sustaining Practices | Person Responsible | Beginning Date | Target Date | Completion Date | Notes
| 35 | Procedures in place for ongoing monitoring / supervision of PSYCKES use (use PSYCKES Usage Reports)
| 36 | PSYCKES use is integrated into relevant program checklists and procedures
| 37 | Procedures are in place for ongoing training of new staff who join organization
| 38 | Procedures are in place for granting access to new staff and deactivitating tokens of departing staff or those that no longer need access
This is an optional tool that may help plan and achieve PSYCKES Implementation. Many of the tasks listed can be accomplished simultaneously; it is not necessary to adhere to the order in which tasks are listed. If a task is not relevant to your organization, enter "N/A."